## Jira Tasks
Key | Type | Epic | Summary | Description | Priority | Story Points | Sprint | Labels | Dependencies | Acceptance Criteria
MUI-001 | Epic |  | Design System Foundation | Shared design tokens, typography, AG Grid theme, dark/light mode | Critical |  | Sprint 1 | design-system
MUI-002 | Story | Design System Foundation | Create shared design token CSS file | marketsui-design-system/tokens/marketsui-tokens.css with oklch colors for light+dark | Critical | 5 | Sprint 1 | design-system, css |  | All tokens in :root and .dark; importable by both apps
MUI-003 | Task | Design System Foundation | Define core surface tokens | background, foreground, card, popover, muted, accent, destructive | Critical | 3 | Sprint 1 | tokens | MUI-002 | Light=neutral grays; Dark=blue-gray
MUI-004 | Task | Design System Foundation | Define trading tokens | Buy(teal)/Sell(rose-pink), P&L positive/negative, order status colors | Critical | 3 | Sprint 1 | tokens, trading | MUI-002 | Distinct from primary/destructive; visible both modes
MUI-005 | Task | Design System Foundation | Define accent/brand tokens | Primary(electric blue), ring, chart palette, sidebar tokens | High | 2 | Sprint 1 | tokens, brand | MUI-002 | No conflict with trading semantics
MUI-006 | Task | Design System Foundation | Define alert tokens | Success, info, warning with foreground variants | Medium | 2 | Sprint 1 | tokens | MUI-002
MUI-007 | Task | Design System Foundation | Define chart palette | 5 chart colors for Highcharts | Medium | 1 | Sprint 1 | tokens, charts | MUI-002
MUI-008 | Story | Design System Foundation | Configure Tailwind v3 with tokens | tailwind.config.js mapping CSS vars to utilities | Critical | 3 | Sprint 1 | tailwind | MUI-002 | bg-card, text-buy etc. all work
MUI-009 | Task | Design System Foundation | Configure AG Grid theme | themeQuartz.withParams() for light+dark | High | 3 | Sprint 1 | ag-grid | MUI-002 | Matches design system colors
MUI-010 | Story | Design System Foundation | Set up typography | Inter + JetBrains Mono via @fontsource | High | 2 | Sprint 1 | typography
MUI-011 | Story | Design System Foundation | Dark/light mode toggle | Class-based toggle on html element | High | 3 | Sprint 1 | theme | MUI-002 | Persists; all components respond
MUI-020 | Epic |  | React Trading App (shadcn/ui) | React 18 + Vite 7 + shadcn/ui + AG Grid + Highcharts | Critical |  | Sprint 1-3 | react
MUI-021 | Story | React App | Scaffold React app | React 18, Vite 7.3.1, TS 5.6.3, Tailwind 3.4.18 | Critical | 3 | Sprint 1 | react, setup |  | Build succeeds
MUI-022 | Story | React App | Create 16 core shadcn/ui components | Button, Input, Label, Select, Dialog, Badge, Tabs, Switch, Checkbox, Progress, Tooltip, Avatar, Separator, Card, Toggle, ToggleGroup | Critical | 8 | Sprint 1 | react, shadcn | MUI-021 | All render correctly both modes
MUI-023 | Story | React App | Create 17 extended shadcn/ui components | Alert, AlertDialog, Popover, DropdownMenu, Slider, ScrollArea, Skeleton, RadioGroup, Textarea, Accordion, Collapsible, HoverCard, Calendar, Toast, Table, Sheet, AspectRatio | High | 13 | Sprint 2 | react, shadcn | MUI-022 | All functional with demos
MUI-024 | Story | React App | Build Header | Logo, search pill, icon buttons, theme toggle, ticker bar with live data | Critical | 5 | Sprint 1 | react, header | MUI-022 | Ticker updates live; pulse dot
MUI-025 | Story | React App | Build tab navigation | 9 tabs + keyboard shortcuts 1-9, ?, N, L | Critical | 3 | Sprint 1 | react, nav | MUI-024 | Underline indicator; shortcut overlay
MUI-026 | Story | React App | Build Market Data Context | Simulated live treasury, corp bond, CDX, futures data | Critical | 5 | Sprint 1 | react, data |  | 2s updates; start/stop
MUI-027 | Story | React App | Build Overview Panel | 5 KPI cards with sparklines, yield curve, benchmarks, positions, orders | Critical | 8 | Sprint 2 | react, dashboard | MUI-026 | Expandable KPIs; gradient chart fill
MUI-028 | Story | React App | Build Rates Panel | AG Grid, yield curve, spreads, KRD chart | High | 8 | Sprint 2 | react, rates | MUI-026 | Row selection; right-aligned numerics
MUI-029 | Story | React App | Build Credit Panel | 3 AG Grids: Corp bonds, CDX, CDS | High | 8 | Sprint 2 | react, credit | MUI-026 | IG/HY counts; consistent styling
MUI-030 | Story | React App | Build Futures Panel | Treasury + SOFR AG Grids; SOFR forward curve chart | High | 8 | Sprint 2 | react, futures | MUI-026 | 32nds price format
MUI-031 | Story | React App | Build Risk Panel | KPIs, DV01 chart, donut, limits, VaR, stress scenarios | High | 8 | Sprint 2 | react, risk | MUI-026 | Fits single screen
MUI-032 | Story | React App | Build Positions Panel | KPIs, filter chips, AG Grid, DV01 chart, detail sidebar | High | 8 | Sprint 2 | react, positions | MUI-026 | Pinned total row
MUI-033 | Story | React App | Build Order Blotter | AG Grid, status filter chips, detail sidebar, +New Order | High | 8 | Sprint 2 | react, blotter | MUI-026 | Oblong pill badges
MUI-034 | Story | React App | Build Order Ticket | Dialog with BUY/SELL, search, inputs, dropdowns, settlement, fixed header/footer | Critical | 8 | Sprint 2 | react, order-ticket | MUI-022 | Scrollable content; confirmation state
MUI-035 | Story | React App | Build Design System Panel | Token table with swatches, typography, spacing, radius, shadows | Medium | 5 | Sprint 3 | react, docs | MUI-002 | 50+ tokens; responsive to theme
MUI-036 | Story | React App | Build Components Panel | 32 interactive demos of all shadcn/ui components | Medium | 8 | Sprint 3 | react, showcase | MUI-023 | All 32 sections
MUI-037 | Story | React App | Implement draggable panels | react-grid-layout for Dashboard, Risk, Positions | Medium | 5 | Sprint 3 | react, layout |  | Drag + resize
MUI-038 | Task | React App | Real-time flash animations | CSS flash on ticker/benchmark value changes | Low | 3 | Sprint 3 | react, animation | MUI-026 | 600ms green/red flash
MUI-039 | Task | React App | Keyboard shortcuts | ? overlay, 1-9 tabs, N blotter, L theme | Low | 2 | Sprint 3 | react, ux | MUI-025 | Excludes focused inputs
MUI-050 | Epic |  | Angular Trading App (spartan/shadcn) | Angular 20 + spartan-style Tailwind components + AG Grid + Highcharts | Critical |  | Sprint 1-3 | angular
MUI-051 | Story | Angular App | Scaffold Angular 20 app | TS 5.8.3, Tailwind 3.4.18, Highcharts Angular | Critical | 3 | Sprint 1 | angular, setup |  | ng build succeeds
MUI-052 | Story | Angular App | Create 8 core spartan components | hlmBtn, hlmInput, hlm-badge, hlm-card, hlm-separator, hlm-progress, hlm-dialog, hlm-textarea | Critical | 8 | Sprint 1 | angular, spartan | MUI-051 | CVA variants; signals
MUI-053 | Story | Angular App | Create 16 extended spartan components | Alert, AlertDialog, Skeleton, Slider, RadioGroup, Accordion, ScrollArea, Table, Sheet, HoverCard, Popover, DropdownMenu, AspectRatio, Calendar, Toast | High | 13 | Sprint 2 | angular, spartan | MUI-052 | All functional
MUI-054 | Story | Angular App | Build Header | Matches React header pixel-for-pixel | Critical | 5 | Sprint 1 | angular, header | MUI-052
MUI-055 | Story | Angular App | Build tab navigation + shortcuts | 9 tabs, @HostListener keyboard shortcuts, ? overlay | Critical | 3 | Sprint 1 | angular, nav | MUI-054
MUI-056 | Story | Angular App | Build Market Data Service | Injectable with Angular signals | Critical | 5 | Sprint 1 | angular, data |  | signal/computed; 2s interval
MUI-057 | Story | Angular App | Build all 7 trading panels | Overview, Rates, Credit, Futures, Risk, Positions, Blotter | Critical | 40 | Sprint 2 | angular, trading | MUI-056 | Match React exactly
MUI-058 | Story | Angular App | Build Order Ticket | hlm-dialog with signals-based form | Critical | 8 | Sprint 2 | angular, order-ticket | MUI-052 | Matches React ticket
MUI-059 | Story | Angular App | Build Design System Panel | Matches React panel exactly | Medium | 5 | Sprint 3 | angular, docs | MUI-002 | Same tokens, same order
MUI-060 | Story | Angular App | Build Components Panel | 32 demos matching React order | Medium | 8 | Sprint 3 | angular, showcase | MUI-053 | All 32 sections
MUI-061 | Task | Angular App | Flash animations | effect() triggers on value changes | Low | 3 | Sprint 3 | angular, animation | MUI-056
MUI-070 | Epic |  | Angular PrimeNG Trading App | Angular 20 + PrimeNG 19 exclusive components | High |  | Sprint 2-3 | angular, primeng
MUI-071 | Story | PrimeNG App | Scaffold PrimeNG app | Angular 20, PrimeNG 19, Tailwind v3, Aura dark preset | High | 5 | Sprint 2 | primeng, setup |  | Build succeeds; theme applied
MUI-072 | Story | PrimeNG App | Build all trading panels | Using p-button, p-table, p-select, p-dialog, p-progressbar, p-tag, p-selectbutton, pInputText, p-inputnumber, pTooltip | High | 40 | Sprint 2-3 | primeng, trading | MUI-071 | No native HTML interactive elements
MUI-073 | Story | PrimeNG App | Build Order Ticket | p-dialog + p-selectbutton + p-select + p-inputnumber | High | 8 | Sprint 3 | primeng, order-ticket | MUI-071
MUI-074 | Story | PrimeNG App | Build Design System + Components panels | p-table for tokens; 24 PrimeNG component demos | Medium | 8 | Sprint 3 | primeng, showcase | MUI-071
MUI-080 | Epic |  | Cross-cutting Concerns | Quality, consistency, polish | High |  | Sprint 3 | quality
MUI-081 | Story | Cross-cutting | Right-align numeric columns | All AG Grid numeric columns across all apps | Medium | 3 | Sprint 3 | ag-grid |  | Prices, yields, P&L right-aligned
MUI-082 | Story | Cross-cutting | Visual consistency audit | React vs Angular pixel comparison | High | 5 | Sprint 3 | quality |  | No significant differences
MUI-083 | Story | Cross-cutting | Oblong pill badges | Side/Status badges in blotter | Medium | 2 | Sprint 3 | ag-grid, ux |  | Min-width, proper padding
MUI-084 | Task | Cross-cutting | Performance audit | <2s load, AG Grid virtualization, chart rendering | Medium | 3 | Sprint 3 | performance |  | Lighthouse >80
MUI-085 | Task | Cross-cutting | Accessibility audit | Keyboard nav, ARIA labels, color contrast | Low | 3 | Sprint 3 | a11y |  | WCAG AA compliant

## Summary
Metric | Count | Story Points
Total Tasks | 54
Epics | 5
Stories | 38 | 301
Tasks | 11 | 28
By Priority
Critical | 21 | 126
High | 18 | 142
Medium | 11 | 50
Low | 4 | 11